## Sheet1
TASKS	ETA	Comments
Created application named as “we_rolls”		Rails App using postgresql database
Devise gem	1 Hour	Devise gem is included for the users and its migration
Rollify gem	1 Hour	Rollify gem is included in app for two different roles .i.e :super_admin & :admin
Models created	3 hours	Models of user, product, product_detail, order, order_detail, product_properties,customer etc
Started working on Shopify_Api gem	2 Hours	Gem has been included and requirement for the gem are added to the app. Migration are pending.
Home controller	1 Hour	Home controller and its index has been created and code for the order has been implemented
Database updated with shopify data	3 hours	Requirements are met. #1- Order Number => order_uuid(order_details), #2- Sku => sku(product_details), #3- Properties => id, name, quatity, price(product_details), #4- Shipping Title => shipping_title(order_details), #5- Order Date => order_date(order_details), #6-Product Name => name(product_details), #7- Status of order => null(order_details{But will be changes at run time}), #6-Payment Status => payment_status(order_details), #8 Customer Email => customer_email(order_details), #9 Customer Phone => customer_phone => (order_details)
Adding home page file to application	2 Hours	Modification of given file according to our requirement
Adding login page to application	2 Hours	Modification of given file according to our requirement
Setting routing for admin and super_admin	2 Hours	Different views for different users that is super_admin, admin
Setting up all order listing and views	6 hours	Setting of order listing according to kamran
Order views for different users	6 hours	Order managing and order operations according to requirements
Finalizing the project	3 hours	Overall testing and functionality